## Gap Analysis Tracker
ISO 27001:2022 Gap Analysis Report - AcmeTech Solutions Pvt Ltd
Analysis Date: 02-Feb-2026
Gap Analysis Summary: | Compliant: 0 | Non Compliant: 11 | Partially Compliant: 17
Control ID | Control Name | Requirement (What ISO says) | Current Status | Gap Description | Remediation Plan
A.5.1 | Policies for information security | Information security policies and topic-specific policies shall be defined, approved by management, published, communicated to and acknowledged by relevant personnel and relevant interested parties. | Non Compliant | Generic IT policy from 3 years ago (IT_Policy_2021.pdf), not aligned with ISO 27001:2022, not communicated recently; no employee acknowledgement logs. | Review and update all policies to align with ISO 27001:2022. Implement DocuSign for employee policy acknowledgement. Schedule annual policy reviews.
A.5.7 | Threat intelligence | Information relating to information security threats shall be collected and analysed to produce threat intelligence. | Non Compliant | No structured threat intel; IT scans news and vendor emails ad-hoc. No formal process to gather threat intelligence. | Subscribe to CERT-In and CISA alerts. Assign IT Security Lead to review threat intelligence weekly and maintain a threat log.
A.5.9 | Inventory of information and other associated assets | Assets associated with information (laptops, mobiles) must be identified and an inventory drawn up. | Partially Compliant | Asset register exists in Excel (10 critical assets documented) but no comprehensive tracking for all 55 laptops and mobile devices; no centralized management. | Implement a centralized Asset Management Tool (Snipe-IT or master SharePoint list). Tag all assets with ID numbers. Quarterly asset audits.
A.5.10 | Acceptable use of information and other associated assets | Rules for the acceptable use and procedures for handling information and other associated assets shall be identified, documented and implemented. | Non Compliant | No formal Acceptable Use Policy (AUP) exists. Informal understanding only. | Develop and publish Acceptable Use Policy covering email, internet, BYOD, and data handling. Require employee acknowledgement.
A.5.15 | Access control | Rules to control physical and logical access to information and other associated assets. | Partially Compliant | Basic access controls exist (VPN, security groups) but no comprehensive Access Control Policy documented. | Document Access Control Policy covering logical and physical access principles, roles, and procedures.
A.5.18 | Access rights | Access rights to information and other associated assets shall be provisioned, reviewed, modified and removed in accordance with the organization's topic-specific policy on and rules for access control. | Partially Compliant | Access provisioned via Servicenow tickets for onboarding; offboarding delays 3-5 days. No periodic access review process for SaaS tools, AD, HRMS. | Implement formal access request workflow in Servicenow Service Desk. Conduct quarterly access reviews for all systems. Same-day offboarding for access revocation.
A.5.23 | Information security for use of cloud services | Processes for acquisition, use, management and exit from cloud services shall be established in accordance with the organization's information security requirements. | Non Compliant | AWS used for production but no cloud governance policy. Potential shadow IT risk. | Develop Cloud Services Policy. Implement approval workflow for new cloud services. Consider CASB or restrict root access permissions.
A.6.1 | Screening | Background verification checks on all candidates prior to employment. | Non Compliant | No formal background check process for employees (55 total staff). HR conducts informal reference checks only. | HR to contract a 3rd party background verification vendor. Update Hiring Policy to mandate background checks for all new hires.
A.6.2 | Terms and conditions of employment | Employment contracts must state responsibilities for information security. | Partially Compliant | Employment contracts exist (HR records) but do not explicitly mention information security, data privacy, or confidentiality responsibilities. | Legal team to add 'Information Security Clause' to all new offer letters and employment contracts. Retrospective addendum for existing staff.
A.6.3 | Information security awareness and training | Employees must receive security training upon hiring and regularly thereafter. | Non Compliant | Ad-hoc training only (T-01: 15 IT staff in June 2025, T-02: 10 support in Aug 2025, T-03: 5 mgmt in Nov 2025). No onboarding training. Only 30/55 employees trained (54.5% coverage). | Implement mandatory 'Security Awareness & Phishing' module (KnowBe4 or similar) for Day 1 orientation. Annual refresher training for all staff with assessments.
A.6.4 | Disciplinary process | Organizations must establish a clear, fair, and effective disciplinary process to enforce information security policies. | Partially Compliant | General HR disciplinary process exists but no specific security violation escalation procedures documented. | Update Disciplinary Policy to include security incident violations and consequences. Communicate to all staff.
A.6.7 | Remote working | Remote working arrangements should not compromise the confidentiality, integrity, or availability of information. | Partially Compliant | Hybrid work model (40% remote). VPN in use but MFA not enforced. No formal remote working security policy. Basic DNS filtering at office only, nothing for remote endpoints. | Implement organization-wide MFA for VPN and all remote access. Deploy endpoint protection to all remote devices. Document Remote Working Security Policy.
A.7.2 | Physical entry | Security perimeters and entry controls shall be defined and managed to protect areas that contain information and other associated assets. | Partially Compliant | HQ office has basic access control (visitor log) but no biometric system or badge access. | Implement badge/biometric access system for HQ. Quarterly review of access logs.
A.7.4 | Physical security monitoring | Premises shall be continuously monitored for unauthorized physical access. | Non Compliant | No CCTV system at HQ office currently. | Install CCTV system with 30-day retention. Monitor server room and main entry points.
A.7.7 | Clear desk and clear screen | Clear desk rules for papers and removable storage media and clear screen rules for information processing facilities shall be defined and appropriately enforced. | Non Compliant | No clear desk policy. Workstations often left unlocked when unattended. | Enforce 5-minute auto-lock via Group Policy (GPO). Implement Clear Desk Policy. Conduct monthly spot checks.
A.8.2 | Return of assets | All employees must return organizational assets upon termination of employment. | Partially Compliant | Offboarding process exists in Servicenow but no formal sign-off collected from employee confirming asset return. | Update Offboarding Checklist to include 'Asset Return Receipt' signature field. IT to verify all assets returned before final settlement.
A.8.3 | Information access restriction | Access to information and other associated assets shall be restricted in accordance with the topic-specific policy on access control. | Partially Compliant | Basic restrictions via AD groups but excessive privileges observed (HR folder accessible to all IT staff). | Apply principle of least privilege. Restrict HR folder permissions to 'HR Group' only. Remove 'Domain Users' broad access.
A.8.5 | Secure authentication | Secure authentication technologies and procedures shall be implemented based on information access restrictions and the topic-specific policy on access control. | Non Compliant | No Multi-Factor Authentication (MFA) on Microsoft 365 email accounts. Weak password hygiene noted (Risk R-01). | Enforce MFA for all users via Microsoft Entra ID (Conditional Access policies). Implement password complexity requirements.
A.8.9 | Configuration management | Configurations, including security configurations, of hardware, software, services and networks shall be established, documented, implemented, monitored and reviewed. | Non Compliant | AWS instances built manually; no standard hardening baseline or configuration management process. No documentation of baseline configurations. | Adopt CIS Benchmarks for server hardening. Use Infrastructure-as-Code (Terraform/Ansible) for automated deployment. Document baseline configurations.
A.8.10 | Information deletion | Information shall be deleted when no longer required, in accordance with documented procedures. | Non Compliant | No defined retention schedule or data deletion procedures. Ad-hoc deletion only. | Develop and implement Data Retention and Deletion Policy aligned with DPDP Act 2023. Schedule periodic data purges.
A.8.12 | Data backup | Backup copies of information, software and system images shall be maintained and tested regularly in accordance with agreed backup policy. | Partially Compliant | Daily backups to S3, weekly restore test documented. However, no formal Backup Policy exists and backups in single region only (Risk R-04). | Document comprehensive Backup Policy. Implement multi-region backup replication. Maintain monthly restore test records.
A.8.16 | Monitoring activities | Networks, systems and applications shall be monitored for anomalous behaviour and appropriate action taken to evaluate potential information security incidents. | Partially Compliant | CloudWatch and M365 logs enabled but no central SIEM or structured alert triage process. Monitoring is reactive. | Implement centralized logging and SIEM solution. Define alerting thresholds and incident escalation procedures.
A.8.23 | Web filtering | Access to external websites shall be managed to reduce exposure to malicious content. | Partially Compliant | Basic DNS filtering at HQ office only. No web filtering for remote endpoints (40% of workforce). | Deploy endpoint-level web filtering solution (DNS-based like Cisco Umbrella) for all devices including remote workers.
A.8.28 | Secure coding | Secure coding principles shall be applied to software development. | Partially Compliant | Code reviews conducted via Git pull requests. However, no secure coding checklist, guidelines, or developer training exists. | Develop Secure Coding Guidelines based on OWASP Top 10. Provide secure coding training to all developers. Implement SAST tools.
A.8.34 | Logging and monitoring | Logs recording user activities, exceptions, faults and information security events shall be produced, stored, protected and analysed. | Partially Compliant | Most critical systems log (AWS CloudWatch, M365 audit logs). However, logs retained only 30 days and no log protection mechanisms. | Extend log retention to minimum 90 days (ideally 1 year for compliance). Implement log integrity controls and centralized log management.
A.8.35 | Incident management | Information security incidents shall be managed in a consistent and effective manner. | Partially Compliant | Servicenow used for incident tracking (Risk R-08) but no formal incident response procedure, severity classification, or escalation matrix. | Develop and document Incident Response Plan with severity levels, roles, escalation procedures, and communication templates. Conduct tabletop exercises.
A.8.36 | Business continuity for information | Information processing facilities shall be implemented with redundancy sufficient to meet availability requirements. | Partially Compliant | IT DR runbook draft exists for AWS infrastructure. However, no comprehensive Business Impact Analysis (BIA) or Business Continuity Plan (BCP) conducted. | Conduct full BIA for all critical processes. Develop and test comprehensive BCP. Define RPO/RTO targets.
A.8.37 | Redundancy | Information processing facilities shall be implemented with redundancy sufficient to meet availability requirements. | Partially Compliant | Production environment is multi-AZ in AWS (good availability). However, backups stored in same region only (single point of failure - Risk R-04). | Implement cross-region backup replication. Document redundancy architecture and failover procedures.