## Risk Register
Risk ID | Asset ID | Risk Description | Threat / Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Risk Level | Control Requirements | Mitigation Plan | Mitigating Resources | Timeline
R-01 | A-01 | Unauthorized access to customer DB via compromised creds | Weak password hygiene, missing enforced MFA | 3 | 5 | 15 | Critical | VPN for admins, security group restrictions | Implement mandatory MFA for all database admin accounts; enforce strong password policy (min 12 chars, complexity); conduct quarterly access reviews; implement privileged access management (PAM) solution | IAM, DB | 1 Week
R-02 | A-03 | Malware/Ransomware on laptops | Users install unverified software, no EDR on all hosts | 4 | 4 | 16 | Critical | Basic AV on ~70% devices, Windows updates monthly | Deploy EDR solution across all 55 laptops within 7 days; implement application whitelisting; enforce monthly security patching; conduct quarterly vulnerability scans; provide endpoint security training | EDR, Workday | 1 Week
R-03 | A-04 | Leakage of employee PII from HRMS | Excessive HRMS roles, no periodic access review | 2 | 4 | 8 | Medium | Vendor provides SSO, HR uses unique accounts | Implement role-based access control (RBAC) review every 6 months; reduce HRMS admin accounts to 2-3 only; enable audit logging; establish access request/approval workflow via ITSM platforms | IAM | 3 Weeks
R-04 | A-09 | Backups unavailable after major AWS outage | Backups only in one region | 2 | 5 | 10 | High | Daily backups, monthly restore test | Implement cross-region backup replication to AWS Singapore region; test disaster recovery annually; document backup restoration procedures; consider multi-cloud backup strategy | Backup, Storage, Cloud, Server | 2 Weeks
R-05 | A-07 | Visitor gains access to internal network | Shared Wi-Fi password, no strong NAC | 3 | 3 | 9 | High | Guest Wi-Fi SSID, WPA2-PSK only | Implement 802.1X network access control (NAC); separate guest Wi-Fi with isolated VLAN; require registration for guest access; deploy firewall rules between guest and internal networks | Network, Server, Cloud | 2 Weeks
R-06 | A-02 | Source code repo exfiltration by disgruntled dev | Offboarding delays, no DLP on endpoints | 2 | 5 | 10 | High | Role-based access in Git, Servicenow tickets for changes | Automate offboarding process to revoke access within 1 hour; implement DLP on endpoints; conduct code review audits; enable Git commit signing; quarterly access certification for repositories | IAM | 2 Weeks
R-07 | A-06 | Phishing leads to account compromise | Basic awareness, no phishing simulations | 4 | 3 | 12 | High | SPF/DKIM/DMARC, email spam filter | Conduct monthly phishing simulation campaigns; implement security awareness training (quarterly); deploy advanced email security solution; enable Conditional Access policies in M365 | Security, M365, Workday | 2 Weeks
R-08 | A-08 | Incomplete incident records impact forensics | No incident classification or templates | 2 | 2 | 4 | Low | Ad-hoc tickets in Servicenow | Develop incident classification matrix (P1-P4); create incident response templates in Servicenow; train support team on documentation requirements; implement automated incident workflow | ITSM | 4 Weeks

## Servicenow Tickets
Number | Assigned To | Approval | Priority | State | Requested For | Short Description | Description | Work Notes
SCTASK0010003 | Kedar Pavaskar | Approved | 1 | Closed Complete | Vinay Kumar | Unauthorized access to customer DB via compromised creds | Weak password hygiene, missing enforced MFA | Implement mandatory MFA for all database admin accounts; enforce strong password policy (min 12 chars, complexity); conduct quarterly access reviews; implement privileged access management (PAM) solution
SCTASK0010004 | Vinay Kumar | Approved | 1 | Closed Complete | Kedar Pavaskar | Malware/Ransomware on laptops | Users install unverified software, no EDR on all hosts | Deploy EDR solution across all 55 laptops within 7 days; implement application whitelisting; enforce monthly security patching; conduct quarterly vulnerability scans; provide endpoint security training
SCTASK0010005 | Vinay Kumar | Requested | 3 | Work in Progress | Kedar Pavaskar | Leakage of employee PII from HRMS | Excessive HRMS roles, no periodic access review | Implement role-based access control (RBAC) review every 6 months; reduce HRMS admin accounts to 2-3 only; enable audit logging; establish access request/approval workflow via ITSM platforms
SCTASK0010006 | Kedar Pavaskar | Approved | 2 | Pending | Vinay Kumar | Backups unavailable after major AWS outage | Backups only in one region | Implement cross-region backup replication to AWS Singapore region; test disaster recovery annually; document backup restoration procedures; consider multi-cloud backup strategy
SCTASK0010007 | Vinay Kumar | Approved | 2 | Pending | Kedar Pavaskar | Visitor gains access to internal network | Shared Wi-Fi password, no strong NAC | Implement 802.1X network access control (NAC); separate guest Wi-Fi with isolated VLAN; require registration for guest access; deploy firewall rules between guest and internal networks
SCTASK0010008 | Kedar Pavaskar | Approved | 2 | Pending | Vinay Kumar | Source code repo exfiltration by disgruntled dev | Offboarding delays, no DLP on endpoints | Automate offboarding process to revoke access within 1 hour; implement DLP on endpoints; conduct code review audits; enable Git commit signing; quarterly access certification for repositories
SCTASK0010009 | Vinay Kumar | Approved | 2 | Pending | Kedar Pavaskar | Phishing leads to account compromise | Basic awareness, no phishing simulations | Conduct monthly phishing simulation campaigns; implement security awareness training (quarterly); deploy advanced email security solution; enable Conditional Access policies in M365
SCTASK0010010 | Kedar Pavaskar | Not Yet Requested | 4 | Open | Vinay Kumar | Incomplete incident records impact forensics | No incident classification or templates | Develop incident classification matrix (P1-P4); create incident response templates in Jira; train support team on documentation requirements; implement automated incident workflow